## Figure 6.16
New Product Introduction (Figure 6.16)
To simplify the process, we will assume that at most one rework cycle may be needed. The modified network is given below.
| Prob of beta test success = | 0.75 | 0.098546
|  |  | Duration Estimates (wks) |  | Expected
Task ID | Description | Predecessors | Optimistic | Pessimistic | Duration | Variance | Random #
A | Lease Mfg/Office space | START | 2 | 4 | 3 | 0.11111 | 0.0010223
B | Identify/hire staff | START | 2 | 3 | 2.5 | 0.027778 | 0.83003
C | Design of physical unit | A, B | 10 | 15 | 12.5 | 0.69444 | 0.13487
D | Electronics design | A, B | 3 | 8 | 5.5 | 0.69444 | 0.87714
E | Software | D | 6 | 12 | 9 | 1 | 0.084133
F | Assemble prototype | C, E | 3 | 4 | 3.5 | 0.027778 | 0.13421
G | Beta test prototype | F | 5 | 5 | 5 | 0 | 0.9081
H | Rework if beta test fails | G | 20 | 25 | 22.5 | 0.69444 | 0.79614
END | End of project | G, H | 0 | 0 | 0 | 0 | 0.90665
Notes:
Task A: (Lease mfg/office space): Performed by project manager
Task B: (Identify/hire staff) performed by HR folks
Task C: (Design of the physical unit) is performed by 2 mechanical engineers whose time is billed at $1600/wk (each engineer)
Task D: (Electronics Design) is performed by 3 electrical engineers (each billed at $1750/wk) and 1 technician ($800/wk)
Task E: (Software) is subcontracted to software development firm for fixed cost of $25,000
Task F: (Assemble prototype) is performed by task C and D engineers and technician (billed at same rate)
Task G: (Beta test prototype) is performed testing group (billed at $1400/wk)
Task H: (Beta test rework) is performed by engineering design group ($9250/week) and testing group ($1400/wk)
Direct Labor Cost Calculations
Task ID | Description | Duration (wks) | Early start time | Early finish time | Latest finish time | Total Slack | Mech Eng cost | Electrical Eng cost | Technician cost | Testing Group
A | Lease Mfg/Office space | 2.002 | 0 | 2.002 | 2.83 | 0.82799
B | Identify/hire staff | 2.83 | 0 | 2.83 | 2.83 | 0
C | Design of physical unit | 10.6743 | 2.83 | 13.5044 | 16.7205 | 3.2162 | 34157.8462
D | Electronics design | 7.3857 | 2.83 | 10.2157 | 10.2157 | 0 |  | 38774.8337 | 5908.5461
E | Software | 6.5048 | 10.2157 | 16.7205 | 16.7205 | 0 | 25000
F | Assemble prototype | 3.1342 | 16.7205 | 19.8547 | 19.8547 | 0 | 10029.4806 | 16454.6166 | 2507.3701
G | Beta test prototype | 5 | 19.8547 | 24.8547 | 24.8547 | 0 |  |  |  | 7000
H | Rework if beta test fails | 0 | 24.8547 | 24.8547 | 24.8547 | 0 | 0 | 0 | 0 | 0
END | End of project | 0 | 24.8547 | 24.8547 | 24.8547
Run | Expected Project Makespan | Expected Direct Costs | t(A) | t(B) | t(c) | t(D) | t(E) | t(F) | t(G) | t(H)
1 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
2 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
3 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
4 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
5 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
6 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
7 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
8 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
9 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
10 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
11 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
12 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
13 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
14 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
15 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
16 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
17 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
18 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
19 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
20 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
21 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
22 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
23 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
24 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
25 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
26 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
27 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
28 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
29 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
30 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
31 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
32 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
33 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
34 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
35 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
36 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
37 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
38 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
39 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
40 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
41 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
42 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
43 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
44 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
45 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
46 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
47 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
48 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
49 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
50 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
51 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
52 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
53 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
54 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
55 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
56 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
57 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
58 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
59 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
60 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
61 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
62 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
63 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
64 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
65 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
66 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
67 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
68 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
69 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
70 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
71 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
72 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
73 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
74 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
75 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
76 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
77 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
78 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
79 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
80 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
81 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
82 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
83 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
84 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
85 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
86 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
87 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
88 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
89 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
90 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
91 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
92 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
93 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
94 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
95 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
96 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
97 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
98 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
99 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
100 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
101 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
102 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
103 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
104 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
105 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
106 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
107 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
108 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
109 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
110 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
111 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
112 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
113 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
114 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
115 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
116 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
117 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
118 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
119 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
120 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
121 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
122 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
123 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
124 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
125 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
126 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
127 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
128 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
129 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
130 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
131 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
132 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
133 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
134 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
135 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
136 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
137 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
138 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
139 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
140 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
141 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
142 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
143 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
144 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
145 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
146 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
147 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
148 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
149 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
150 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
151 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
152 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
153 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
154 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
155 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
156 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
157 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
158 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
159 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
160 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
161 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
162 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
163 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
164 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
165 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
166 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
167 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
168 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
169 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
170 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
171 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
172 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
173 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
174 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
175 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
176 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
177 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
178 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
179 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
180 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
181 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
182 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
183 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
184 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
185 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
186 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
187 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
188 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
189 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
190 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
191 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
192 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
193 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
194 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
195 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
196 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
197 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
198 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
199 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
200 | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
Mean | 24.8547 | 139832.6933 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1
St Dev | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D78: Binary variable indicating if task A is on the CP (=1) or not (=0)
START
Lease Mfg/Office Space
Identify/hire staff
Design of physical unit
Electronics design
Software
Assemble prototype
Beta test prototype
END
Beta test fails (with probability of 0.25) and rework is needed
Beta test fails (with probability of 0.25) and rework is needed
START
Lease Mfg/Office Space
Identify/hire staff
Design of physical unit
Electronics design
Software
Assemble prototype
Beta test prototype
END
Beta test fails and rework is needed
Prob = .25
Prob = .75