## Proj Portfolio Example
This is an example of a ranking/scoring questionnaire that was used to evaluate the merits (or lack therof) of a proposed project:
Attribute |  |  |  |  | Measurement Scale |  |  | Attribute Weight (wi)
1) Does project increase market share? |  |  | unlikely |  |  |  | likely | 30%
2) Is new facility needed? |  |  |  |  | yes no |  |  | 15%
3) Are there safety concerns? |  |  |  | likely | unsure | no |  | 10%
4) Likelihood of successful technical development? |  |  | unlikely |  |  |  | likely | 20%
5) Likelihood of successful commercial development? |  |  | unlikely |  |  |  | likely | 25%
In the below table, typical responses to the five questions in Figure 2.13 are given; these responses were then converted
converted to a common (0, 1) scale using a linear and an exponential transformation so that a single ranking could be calculated
for each proposed project.
| Upper bound (U) = | 5 | Lower Bound (L) = |  | 1
| Attribute | #1 | #2 | #3 | #4 | #5 | Project Score (Vj)
| Project A | 4 | yes | likely | 4 | 1
| Project B | 2 | no | unsure | 3 | 4
Linear Scale
| Project A | 0.75 | 0 | 0 | 0.75 | 0 | 0.375
| Project B | 0.25 | 1 | 0.5 | 0.5 | 0.75 | 0.5625
Exponential Scale
| Project A | 0.96794 | 0 | 0 | 0.96794 | 0 | 0.48397
| Project B | 0.64391 | 1 | 0.8808 | 0.8808 | 0.96794 | 0.8494
Assume that you can fund all or part of projects A and/or B. To decide the level of funding, we can define a Solver model
that determines decision variables xA and xB, where
xA = percent of project A that is funded
xB = percent of project B that is funded
Assuming that the value of a project is determined by the project score (given in the above table) times the percent funded,
we want to maximize the total project portfolio score that is equal to VA xA + VB xB subject to the budget constraints
Y e a r (t)
|  | 1 | 2 | 3 | 4
| Project A | -40 | 10 | 20 | 20
| Project B | -65 | -25 | 50 | 50
| Budget Constraint (Bt) | 120 | 20 | 40 | 55
Annual Cash flow
Percent Funded (Decision Variables) | Value | Year 1 | Year 2 | Year 3 | Year 4 | Project Value
xA | 100% | -40 | 10 | 20 | 20 | 0.375
xB | 100% | -65 | -25 | 50 | 50 | 0.5625
|  | -105 | -15 | 70 | 70 | 0.9375
|  | 105 | 15 | -70 | -70
1 2 3 4 5
1 2 3 4 5
1 2 3 4 5
The project score is calculated by multipying the attribute value times the attribute weight and summing these values
Total portfolio score (to be maximized)