## Slide 1
Notes: 11/29/100
1

## Slide 2: Importance of Project Management
• Projects represent change and allow organizations to effectively introduce new products, new process, new programs
• Project management offers a means for dealing with dramatically reduced product cycle times
• Projects are becoming globalized making them more difficult to manage without a formal methodology
• Project management helps cross-functional teams to be more effective
Notes: 11/29/100
3

## Slide 3: Management of IT Projects
• More than $250 billion is spent in the US each year on approximately 175,000 information technology projects. • Only 26 percent of these projects are completed on time and within budget. • The average cost for a development project for a large company is more than $2 million. • Project management is an $850 million industry and is expected to grow by as much as 20 percent per year.
Bounds, Gene. “The Last Word on Project Management” IIE Solutions, November, 1998.
Notes: 11/29/100
3

## Slide 4: What Defines a Project?
•
•
•
•
•
•
•
How does a project
differ from a
program?
Notes: 11/29/100
2

## Slide 5: Project Management versus Process Management
“Ultimately, the parallels between process and project management give way to a fundamental difference: process management seeks to eliminate variability whereas project management must accept variability because each project is unique.”
Elton, J. & J. Roe. “Bringing Discipline to Project Management” Harvard Business Review, March-April, 1998.
Notes: 11/29/100
2

## Slide 6: Measures of Project Success
•
•
•
•
•
•
•
Was the movie
“Titanic”
a success?
Notes: 11/29/100
2

## Slide 7
Delayed Openings are a Fact of Life in the Foodservice, Hospitality Industry
Disney's shipbuilder was six months late in delivering its new cruise ships, and thousands of customers who had purchased tickets were stranded.
Even with that experience, their second ship was also delivered well after the published schedules. Universal Studios in Orlando, Fla. had been building a new restaurant and entertainment complex for more than two years. They advertised a December opening, only to announce in late November that it would be two or three months late.
Even when facilities do open close to schedule, they are rarely finished completely and are often missing key components. Why do those things happen? With all of the sophisticated computers and project management software, why aren't projects completed on schedule?
Frable, F. Nation's Restaurant News (April 12, 1999)

## Slide 8: IT Project Outcomes
26%
29%
6%
16%
9%
8%
6%
Source: Standish Group Survey, 1999 (from a survey of 800 business systems projects)

## Slide 9: Why do Projects Fail?
Studies have shown that the following factors contribute significantly to project failure:
• Improper focus of the project management system
• Fixation on first estimates
• Wrong level of detail
• Lack of understanding about project management tools; too much reliance on project management software
• Too many people
• Poor communication
• Rewarding the wrong actions

## Slide 10: Why do IT Projects Fail?
• Ill-defined or changing requirements
• Poor project planning/management
• Uncontrolled quality problems
• Unrealistic expectations/inaccurate estimates
• Naive adoption of new technology
Source: S. McConnell, Construx Software Builders, Inc.

## Slide 11: Have You Ever Lost Sight of the Project Goals?

## Slide 12: Not all Projects Are Alike…
“[in IT projects], if you ask people what’s done and what remains to be done there is nothing to see. In an IT project, you go from zero to 100 percent in the last second--unlike building a brick wall where you can see when you’re halfway done. We’ve moved from physical to non-physical deliverables….”
J. Vowler (March, 2001)
Engineering projects = task-centric
IT projects = resource-centric
Notes: 11/29/100
2

## Slide 13: Shenhar’s Taxonomy of Project Types
De
g
ree
o
f
U
n
cert
ain
t
y/
R
isk
Sys
tem
C
o
m
pl
e
xi
t
y/S
c
op
e
H
ig
h
Low
-
T
e
c
h
A
s
s
em
b
l
y
P
ro
ject
s
A
rr
ay
P
ro
ject
s
Sy
st
e
m
P
ro
ject
s
M
e
d
i
um-
T
e
c
h
H
ig
h-
T
e
c
h
S
u
p
e
r
Hi
gh
-
T
e
c
h
Co
n
s
tr
u
ct
io
n
N
e
w
c
e
ll
pho
n
e
N
e
w
s
h
r
i
n
k
-
w
r
ap
p
e
d
so
ftw
ar
e
ER
P
im
p
l
e
me
n
t
a
ti
on
i
n
m
u
lti-
na
ti
ona
l
fi
r
m
A
ut
o r
e
pa
ir
A
d
van
c
e
d
r
ada
r
sy
st
e
m
Notes: 11/29/100
2

## Slide 14: Project Life Cycle
Time
Phase 1 Phase 2 Phase 3 Phase 4
Formation & Planning Scheduling & Evaluation &
Selection Control Termination
Required Resources
Notes: 11/29/100
2

## Slide 15: Life Cycle Models: Pure Waterfall
Concept Design
Requirements Analysis
Architecture Design
Detailed Design
Coding & Debugging
System Testing
Source: S. McConnell
Rapid Development (Microsoft Press, 1996)
Notes: 11/29/100
2

## Slide 16: Life Cycle Models: Code & Fix
Notes: 11/29/100
2

## Slide 17: Design, Cost, Time Trade-offs
Target
COST
DESIGN
TIME (SCHEDULE)
Due Date
Budget Constraint
Optimal Time-Cost Trade-off
Required Performance
QUALITY

## Slide 18: Optional Scope Contracts
Fixed Scope Contract specifies SCHEDULE, COST, SCOPE
Optional Scope Contract specifies SCHEDULE, COST, QUALITY
(general design guidelines may be indicated)
Since it is widely accepted that you can select three of the four dimensions (or perhaps only two), what to do?
Notes: 11/29/100
2

## Slide 19: Importance of Project Selection
“There are two ways for a business to succeed at new products: doing projects right, and doing the right projects.”
Cooper, R.G., S. Edgett, & E. Kleinschmidt. Research • Technology Management, March-April, 2000.
Notes: 11/29/100
3

## Slide 20: Project Initiation & Selection
• Critical factors
1) Competitive necessity
2) Market expansion
3) Operating requirement
• Numerical Methods
1) Payback period
2) Net present value (NPV) or Discounted Cash Flow (DCF)
3) Internal rate of return (IRR)
4) Expected commercial value (ECV)
• Project Portfolio
1) Diversify portfolio to minimize risk
2) Cash flow considerations
3) Resource constraints
Notes: 11/29/100
3

## Slide 21: Payback Period
Number of years needed for project to repay its initial fixed investment
Example: Project costs $100,000 and is expected to save company $20,000 per year
Payback Period = $100,000 / $20,000 = 5 years
Notes: 11/29/100
3

## Slide 22: Net Present Value (NPV) Discounted Cash Flow (DCF)
Let Ft = net cash flow in period t (t = 0, 1,..., T)
F0 = initial cash investment in time t = 0
r = discount rate of return (hurdle rate)
Notes: 11/29/100
3

## Slide 23: Internal Rate of Return (IRR)
Find value of r such that NPV is equal to 0
Example (with T = 2):
Find r such that
Notes: 11/29/100
3

## Slide 24: DCF Project Example*
*Hodder, J. and H.E. Riggs. “Pitfalls in Evaluating Risky Projects”, Harvard Business Review, Jan-Feb, 1985, pp. 128-136.

## Slide 25: DCF Project Example (cont’d)
What is the internal rate of return for this project?

## Slide 26: DCF Example Continued
What if you can sell the product (assuming that both Research and Product Development AND Market Development are successful) to a third party? What are the risks AT THAT POINT IN TIME?
Assume that discount rate r2 is 5%

## Slide 27: DCF Example Continued
Expected cash flows (with sale of product at end of year 4) are now:
What is the internal rate of return for this project?

## Slide 28: Criticisms of NPV/DCF
1) Assumes that cash flow forecasts are accurate; ignores the “human bias” effect
2) Fails to include effects of inflation in long term projects
3) Ignores interaction with other proposed and ongoing projects (minimize risk through diversification)
4) Use of a single discount rate for the entire project (risk is typically reduced as the project evolves)

## Slide 29: Expected Commercial Value (ECV)
Develop New Product
Technical Failure
Technical Success
Probability = pt
Probability = 1 - pt
Launch New Product
Commercial Failure (with net benefit = 0)
Commercial Success (with net benefit = NPV)
Probability = pc
Probability = 1 - pc
Risk class 1
Risk class 2

## Slide 30: DCF Example Revisited
Discount rate r1
Discount rate r2
Research & Product Development
Development Succeeds
Probability = pt
Development Fails
Probability = 1 - pt
Market Development
Product Demand High
0.3
Product Demand Medium
Product Demand Low
0.5
0.2
Drop project

## Slide 31: Ranking/Scoring Models
Notes: 11/29/100
2

## Slide 32: Scoring Attributes
To convert various measurement scales to a (0, 1) range….
LINEAR SCALE: value of attribute i is
EXPONENTIAL SCALE: value of attribute i is
Notes: 11/29/100
2

## Slide 33: Ranking/Scoring Example
Notes: 11/29/100
2

## Slide 34
Ranking/Scoring Example (cont’d)
Notes: 11/29/100
3

## Slide 35: Analyzing Project Portfolios: Bubble Diagram
Expected NPV
Prob of Commercial Success
High
Zero
Low
High
Notes: 11/29/100
2

## Slide 36: Analyzing Project Portfolios: Product vs Process
Extent of Product Change
Extent of Process Change
Source: Clark and Wheelwright, 1992
Notes: 11/29/100
2

## Slide 37: Key Elements of Project Portfolio Selection Problem
1. Multi-period investment problem
Top management typically allocates funds to different product lines (e.g., compact cars, high-end sedans)
Product lines sell in separate (but not necessarily independent) market segments
Product line allocations are changed frequently
Conditions in each market segment are uncertain from period to period due to competition and changing customer preferences
Notes: 11/29/100
2

## Slide 38: “Stage-Gate” Approach
Installation Plan
Facility Prep
Training Plan Implementation
Detail Design
Schedule & Budget
Contingency Plan
Product & Performance Reviews
Initiation
Define
Design
Control
Improve
Work Statement
Risk Assessment
Purchasing Plan
Change Mgt
Initiation
Project Review
Charter
Source: PACCAR Information Technology Division
Renton, WA
Production close-out
Lessons learned
Post-project audit

## Slide 39: Project Selection Example
Notes: 11/29/100
2

## Slide 40: Phases of Project Management
Project formulation and selection
Project planning
  Summary statement
  Work breakdown structure
  Organization plan
  risk management
  Subcontracting and bidding process
Project scheduling
  Time and schedule
  Project budget
  Resource allocation
  Equipment and material purchases
Monitoring and control
  Cost control metrics
  Change orders
  Milestone reports

## Slide 41: Project Planning
Summary Statement
  Executive summary: mission and goals, constraints
  Description and specifications of deliverables
  Quality standards used (e.g., ISO)
  Role of main contractor and subcontractors
  Composition and responsibilities of project team
Organization Plan
  Managerial responsibilities assigned; signature authority
  Cross impact matrix (who works on what)
  Relationship with functional departments
  Project administration
  Role of consultants
  Communication procedures with organization, client, etc.
Notes: 11/29/100
2

## Slide 42: Importance of Project Planning
The 6P Rule of Project Management:
Prior Planning Prevents Poor Project Performance
“If you fail to plan, you will plan to fail”
Anonymous
Notes: 11/29/100
2

## Slide 43: Work Breakdown Structure (WBS)
1) Specify the end-item “deliverables”
2) Subdivide the work, reducing the dollars and complexity with each additional subdivision
3) Stop dividing when the tasks are manageable “work packages” based on the following:
• Skill group(s) involved
• Managerial responsibility
• Length of time
• Value of task
Notes: 11/29/100
3

## Slide 44: Work Packages/Task Definition
The work packages (tasks or activities) that are defined by the WBS must be:
• Manageable
• Independent
• Integratable
• Measurable
Notes: 11/29/100
3

## Slide 45: Design of a WBS
“The usual mistake PMs make is to lay out too many tasks; subdividing the major achievements into smaller and smaller subtasks until the work breakdown structure (WBS) is a ‘to do’ list of one-hour chores. It’s easy to get caught up in the idea that a project plan should detail everything everybody is going to do on the project. This springs from the screwy logic that a project manager’s job is to walk around with a checklist of 17,432 items and tick each item off as people complete them….”
The Hampton Group (1996)
Notes: 11/29/100
3

## Slide 46: Two-Level WBS
1. Charity Auction
1.1 Event Planning
1.2 Item Procurement
1.3 Marketing
1.4. Corporate Sponsorships
WBS level 1
WBS level 2

## Slide 47: Three-Level WBS
1.1 Event Planning
1.2 Item Procurement
1.3 Marketing
1. Charity Auction
1.4 Corporate Sponsorships
1.1.1 Hire Auctioneer
1.1.2. Rent space
1.1.3 Arrange for decorations
1.2.1 Silent auction items
1.2.2 Live auction items
1.2.3 Raffle items
1.3.1 Individual ticket sales
1.3.2 Advertising
1.1.4 Print catalog
WBS level 1
WBS level 2
WBS level 3

## Slide 48: Estimating Task Durations (cont’d)
• Benchmarking
• Modular approach
• Parametric techniques
• Learning effects
Notes: 11/29/100
3

## Slide 49: Beta Distribution
Completion time of task j
Time
Probability density function

## Slide 50: Beta Distribution
For each task j, we must make three estimates:
most optimistic time
most pessimistic time
most likely time

## Slide 51: Estimating Task Durations: Painting a Room
Task: Paint 4 rooms, each is approximately 10’ x 20’. Use flat paint on walls, semi-gloss paint on trim and woodwork. Each room has two doors and four windows. You must apply masking tape before painting woodwork around the doors and windows. Preparation consists of washing all walls and woodwork (some sanding and other prep work will be needed). Only one coat of paint is necessary to cover existing paint. All supplies will be provided at the start of the task. Previous times on similar painting jobs are indicated in the table below.
What is your estimate of the average time you will need? What is your estimate of the variance?

## Slide 52: Estimating Task Durations with Incentives
Task: Consider the painting job that you have just estimated. Now, however, there are explicit incentives for meeting your estimated times. If you finish painting the room before your specified time, you will receive a $10 bonus payment. HOWEVER, if you finish the painting job after your specified time, you will be fined $1000.
Revised estimated time =
Notes: 11/29/100
4

## Slide 53: Estimating Task Durations with Incentives
Task: Consider the painting job that you have just estimated. Now, however, there are explicit incentives for meeting your estimated times. If you finish painting the room before your specified time, you will receive a $10 bonus payment. If you finish the painting job after your specified time, there is no penalty.
Revised estimated time =
Notes: 11/29/100
4

## Slide 54: Role of Project Manager/Team
Project Manager
Client
Subcontractors
Regulating Organizations
Project Team
Functional Managers
Top Management
Notes: 11/29/100
2

## Slide 55: Responsibilities of a Project Manager
To the organization and top management
• Meet budget and resource constraints
• Engage functional managers
To the project team
• Provide timely and accurate feedback
• Keep focus on project goals
• Manage personnel changes
To the client
• Communicate in timely and accurate manner
• Provide information and control on changes/modifications
• Maintain quality standards
To the subcontractors
• Provide information on overall project status

## Slide 56: Project Team
What is a project team?
A group of people committed to achieve a common set of goals for which they hold themselves mutually accountable
Characteristics of a project team
• Diverse backgrounds/skills
• Able to work together effectively/develop synergy
• Usually small number of people
• Have sense of accountability as a unit

## Slide 57
“I design user interfaces to please an audience of one. I write them for me. If I’m happy, I know some cool people will like it. Designing user interfaces by committee does not work very well; they need to be coherent. As for schedule, I’m not interested in schedules; did anyone care when War and Peace came out?”
Developer, Microsoft Corporation
As reported by MacCormack and Herman, HBR Case 9-600-097: Microsoft Office 2000

## Slide 58: Intra-team Communication
M = Number of project team members
L = Number of links between pairs of team members
If M =2, then L = 1
If M =3, then L = 3

## Slide 59: Number of Intra-team Links
Notes: 11/29/100
3

## Slide 60: Importance of Communication
On the occasion of a migration from the east, men discovered a plain in the land of Shinar, and … said to one another, “Come, let us build ourselves a city with a tower whose top shall reach the heavens….” The Lord said, …“Come, let us go down, and there make such a babble of their language that they will not understand one another’s speech.” Thus, the Lord dispersed them from there all over the earth, so that they had to stop building the city.
Genesis 11: 1-8

## Slide 61: Project Performance and Group Harmony
Two schools of thought:
1) “Humanistic school” -- groups that have positive characteristics will perform well
2) “Task oriented” school -- positive group characteristics detract from group performance
What is the relationship between the design of multidisciplinary project teams and project success?

## Slide 62: Project Performance and Group Harmony (cont’d)
Experiment conducted using MBA students at UW and Seattle U using computer based simulation of pre-operational testing phase of nuclear power plant*
Total of 14 project teams (2 - 4 person project teams) with a total of 44 team members; compared high performance (low cost) teams vs low performance (high cost) teams
Measured: Group Harmony
Group Decision Making Effectiveness
Extent of Individual’s Contributions to Group
Individual Attributes
*Brown, K., T.D. Klastorin, & J. Valluzzi. “Project Management Performance: A Comparison of Team Characteristics”, IEEE Transactions on Engineering Management, Vol 37, No. 2 (May, 1990), pp. 117-125.

## Slide 63: Group Harmony: High vs Low Performing Groups

## Slide 64: Extent of Individual Contribution: High vs Low Performing Groups

## Slide 65: Decision Making Effectiveness: High vs Low Performing Groups

## Slide 66: Project Organization Types
• Functional: Project is divided and assigned to appropriate functional entities with the coordination of the project being carried out by functional and high-level managers
• Functional matrix: Person is designated to oversee the project across different functional areas
• Balanced matrix: Person is assigned to oversee the project and interacts on equal basis with functional managers
• Project matrix: A manager is assigned to oversee the project and is responsible for the completion of the project
• Project team: A manager is put in charge of a core group of personnel from several functional areas who are assigned to the project on a full-time basis
Notes: 11/29/100
2

## Slide 67: Project Organization Continuum
Project Team
Organization
Project Matrix
C o n t i n u u m
Project fully managed by functional managers
Project fully managed by project team manager
Functional
Organization
Functional Matrix
Balanced Matrix
Notes: 11/29/100
2

## Slide 68: A Business School as a Matrix Organization
Dean
Associate Dean for Undergraduate Program
Associate Dean for MBA Programs
Director of Doctoral Program
Accounting Department Chair
Marketing Department Chair
Finance Department Chair
Gloria
Diane
Bob
Zelda
Larry
Curly
Moe
Barby
Leslie
Notes: 11/29/100
2

## Slide 69: Matrix Organizations & Project Success
• Matrix organizations emerged in 1960’s as an alternative to traditional means of project teams
• Became popular in 1970’s and early 1980’s
• Still in use but have evolved into many different forms
• Basic question: Does organizational structure impact probability of project success?
Notes: 11/29/100
2

## Slide 70: Organizational Structure & Project Success
• Studies by Larson and Gobeli (1988, 1989)
• Sent questionnaires to 855 randomly selected PMI members
• Asked about organizational structure (which one best describes the primary structure used to complete the project)
• Perceptual measures of project success: successful, marginal, unsuccessful with respect to :
1) Meeting schedule
2) Controlling cost
3) Technical performance
4) Overall performance
• Respondents were asked to indicate the extent to which they agreed with each of the following statements:
1) Project objectives were clearly defined
2) Project was complex
3) Project required no new technologies
4) Project had high priority within organization
Notes: 11/29/100
2

## Slide 71: Study Data
• Classification of 547 respondents (64% response rate)
30% project managers or directors of project mgt programs
16% top management (president, vice president, etc.)
26% managers in functional areas (e.g., marketing)
18% specialists working on projects
• Industries included in studies
14% pharmaceutical products
10% aerospace
10% computer and data processing products
others: telecommunications, medical instruments, glass products, software development, petrochemical products, houseware goods
• Organizational structures:
13% (71): Functional organizations
26% (142): Functional matrix
16.5% (90): Balanced matrix
28.5% (156): Project matrix
16% (87): Project team
Notes: 11/29/100
2

## Slide 72: ANOVA Results by Organizational Structure
*Statistically significant at a p<0.01 level
Notes: 11/29/100
2

## Slide 73: Summary of Results
• Project structure significantly related to project success
• New development projects that used traditional functional organization had lowest level of success in controlling cost, meeting schedule, achieving technical performance, and overall results
• Projects using either a functional organization or a functional matrix had a significantly lower success rate than the other three structures
• Projects using either a project matrix or a project team were more successful in meeting their schedules than the balanced matrix
• Project matrix was better able to control costs than project team
• Overall, the most successful projects used a balanced matrix, project team, or--especially--project matrix
Notes: 11/29/100
2

## Slide 74: Subcontracting = Business Alliance
When you subcontract part (or all) of a project, you are forming a business alliance....
Intelligent Business Alliances: “A business relationship for mutual benefit between two or more parties with compatible or complementary business interests and/or goals”
Larraine Segil, Lared Presentations
Notes: 11/29/100
2

## Slide 75: Communication and Subcontractors
How is knowledge transferred?
What types of communication mechanism(s) will be used between company and subcontractor(s)?
WHAT a company communicates.....
HOW a company communicates.....
Notes: 11/29/100
2

## Slide 76: Personality Compatibility
Corporate Personality
Subcontractor Personality
Individual Personality
Project
Notes: 11/29/100
2

## Slide 77: Subcontracting Issues
• What part of project will be subcontracted?
• What type of bidding process will be used? What type of contract?
• Should you use a separate RFB (Request for Bids) for each task or use one RFB for all tasks?
• What is the impact on expected duration of project?
• Use a pre-qualification list?
• Incentives? Bonus for finishing early? Penalties for finishing after stated due date?
• What is impact of risk on expected project cost?
Notes: 11/29/100
2

## Slide 78: Basic Contract Types
Fixed Price Contract
  Client pays a fixed price to the contractor irrespective of actual audited cost of project
Cost Plus Contract
  Client reimburses contractor for all audited costs of project (labor, plant, & materials) plus additional fee (that may be fixed sum or percent of costs incurred)
Units Contract
  Client commits to a fixed price for a pre-specified unit of work; final payment is based on number of units produced
Notes: 11/29/100
2

## Slide 79: Incentive (Risk Sharing) Contracts
General Form:
Payment to Subcontractor = Fixed Fee + (1 - B) (Project Cost)
where B = cost sharing rate
Cost Plus Contract
B = 0
B = 1
Fixed Price Contract
Linear & Signalling Contracts
Notes: 11/29/100
2

## Slide 80: Why Use Incentive Contracts?
Expected Cost of Project = $100M
Two firms bid on subcontract
Firm 1 Firm 2
Fixed Fee (bid) $5 M $7 M
Project Cost $105 M $95 M
(inefficient producer)
What is result if Cost Plus Contract (B = 0) used?
Notes: 11/29/100
2

## Slide 81: Washington State Bid Code (WAC 236-48-093)
WAC 236-48-093: A contract shall be awarded to the lowest responsible and responsive bidder based upon, but not limited to, the following criteria where applicable and only that which can be reasonably determined:
1) The price and effect of term discounts...price may be determined by life cycle costing if so indicated in the invitation to bid
2) The conformity of the goods and/or services bid with invitation for bid or request for quotation specifications depicting the quality and the purposes for which they are required.
3) The ability, capacity, and skill of the bidder to perform the contract or provide the services required.
4) The character, integrity, reputation, judgement, experience, and efficiency of the bidder.
5) Whether the bidder can perform the contract with the time specified.
6) The quality of performance on previous contracts for purchased goods or services.
7) The previous and existing compliance by the bidder with the laws relating to the contract for goods and services.
8) Servicing resources, capability, and capacity.
Notes: 11/29/100
2

## Slide 82: Competitive Bidding: Low-Bid System
“In the low-bid system, the owner wants the most building for the least money, while the contractor wants the least building for the most money. The two sides are in basic conflict.”
        Steven Goldblatt
        Department of Building Construction
        University of Washington
        The Seattle Times, Nov 1, 1987
Notes: 11/29/100
2

## Slide 83: Precedence Networks
Networks represent immediate precedence relationships among tasks (also known as work packages or activities) and milestones identified by the WBS
Milestones (tasks that take no time and cost $0 but indicate significant events in the life of the project)
Two types of networks: Activity-on-Node (AON)
Activity-on-Arc (AOA)
All networks: must have only one (1) starting and one (1) ending point
Notes: 11/29/100
2

## Slide 84: Precedence Networks: Activity-on-Node (AON)
A
B
C
D
Start
End
Notes: 11/29/100
2

## Slide 85: Precedence Diagramming
Standard precedence network (either AOA or AON) assumes that a successor task cannot start until the predecessor(s) task(s) have been completed. Alternative relationships can be specified in many software packages:
Finish-to-start (FS = ): Job B cannot start until  days after Job A is finished
Start-to-start (SS = ): Job B cannot start until  days after Job A has started
Finish-to-finish (FF = ): Job B cannot finish until  days after Job A is finished
Start-to-finish (SF = ): Job B cannot finish until  days after Job A has started
Notes: 11/29/100
2

## Slide 86: Critical Path Method (CPM): Basic Concepts
Task A
7 months
Task B
3 months
End
Task C
11 months
Start
Notes: 11/29/100
2

## Slide 87: Critical Path Method (CPM): Basic Concepts
Start
Task A
7 months
Task B
3 months
Task C
11 months
End
ESStart = 0
LFStart = 0
ESA = 0
LFA = 8
ESB = 7
LFB = 11
ESC = 0
LFC = 11
ESEnd = 11
LFEnd = 11
ESj = Earliest starting time for task (milestone) j
LFj = Latest finish time for task (milestone) j
Notes: 11/29/100
2

## Slide 88: AON Precedence Network: Microsoft Project
Notes: 11/29/100
2

## Slide 89: Critical Path Method (CPM): Example 2
Ta
sk
A
14
w
k
s
Ta
sk
D
12
w
k
s
Ta
sk
E
6
w
k
s
Ta
sk
B
9
w
k
s
Ta
sk
C
20
w
k
s
Ta
sk
F
9
w
k
s
START
END
ES
F
=
LF
F
=
ES
D
=
LF
D
=
ES
A
=
LF
A
=
ES
B
=
LF
B
=
ES
END
=
LF
END
=
ES
C
=
LF
C
=
ES
E
=
LF
E
=
Notes: 11/29/100
2

## Slide 90: Example 2: Network Paths
Notes: 11/29/100
2

## Slide 91: Example 2: CPM Calculations
Notes: 11/29/100
2

## Slide 92: Example 2: Calculating Total Slack (TSi)
Total Slack for task i = TSi = LFi - ESi - ti
Notes: 11/29/100
2

## Slide 93: Slack (Float) Definitions (for task i)
Total Slack (TSi) = LFi - ESi - ti
Free Slack (FSi) = ESi,min - ESi - ti
where ESi,min = minimum early start time of all tasks that
immediately follow task i
= min (ESj for all task j  Si)
Safety Slack (SSi) = LFi - LFi,max - ti
where LFi,max = maximum late finish time of all tasks that
immediately precede task i
= min (LFj for all task j  Pi)
Independent Slack (ISi) = max (0, ESi,min - LFi,max - ti)
Notes: 11/29/100
2

## Slide 94: Example #2: LP Model
Decision variables: STARTj = start time for task j
END = ending time of project (END milestone)
Minimize END
subject to
STARTj ≥ FINISHi for all tasks i that immediately precede task j
STARTj ≥ 0 for all tasks j in project
where FINISHi = STARTi + ti = STARTi + duration of task i
Notes: 11/29/100
5

## Slide 95: Example #2: Excel Solver Model
Notes: 11/29/100
5

## Slide 96: Gantt Chart
Microsoft Project 4.0
Notes: 11/29/100
2

## Slide 97: Project Budgeting
• The budget is the link between the functional units and the project
• Should be presented in terms of measurable outputs
• Budgeted tasks should relate to work packages in WBS and organizational units responsible for their execution
• Should clearly indicate project milestones
• Establishes goals, schedules, and assigns resources (workers, organizational units, etc.)
• Should be viewed as a communication device
• Serves as a baseline for progress monitoring & control
• Update on rolling horizon basis
• May be prepared for different levels of aggregation (strategic, tactical, short-range)
Notes: 11/29/100
5

## Slide 98: Project Budgeting (cont’d)
• Top-down Budgeting: Aggregate measures (cost, time) given by top management based on strategic goals and constraints
• Bottom-up Budgeting: Specific measures aggregated up from WBS tasks/costs and subcontractors
Notes: 11/29/100
5

## Slide 99: Issues in Project Budgets
• How to include risk and uncertainty factors?
• How to measure the quality of a project budget?
• How often to update budget?
• Other issues?
Notes: 11/29/100
5

## Slide 100: Critical Path Method (CPM): Example 2
Ta
sk
A
14
w
k
s
Ta
sk
D
12
w
k
s
Ta
sk
E
6
w
k
s
Ta
sk
B
9
w
k
s
Ta
sk
C
20
w
k
s
Ta
sk
F
9
w
k
s
START
END
ES
F
= 26
LF
F
= 35
ES
D
= 14
LF
D
= 26
ES
A
= 0
LF
A
= 14
ES
B
= 0
LF
B
= 14
ES
END
= 35
LF
END
= 35
ES
C
= 0
LF
C
= 29
ES
E
= 26
LF
E
= 35
Notes: 11/29/100
2

## Slide 101: Project Budget Example
Cost for Resource A worker = $400/week
Cost for Resource B worker = $600/week
Notes: 11/29/100
5

## Slide 102: Project Budget Example (cont’d)
W e e k
W e e k
Notes: 11/29/100
5

## Slide 103: Cumulative Costs
Range of feasible budgets
Notes: 11/29/100
5

## Slide 104: Weekly Costs (Cash Flows)
Notes: 11/29/100
5

## Slide 105: Managing Cash Flows
• Want to manage payments and receipts
• Must deal with budget constraints on project and organization requirements (e.g., payback period)
• Organization profitability
Notes: 11/29/100
3

## Slide 106: Cash Flow Example
M1
END
START
Task B
8 mos
Receive payment of $3000
Receive payment of $3000
Make payment of $5000
Task C
4 mos
Task A
2 mos
M2
Task D
8 mos
Task E
3 mos
Notes: 11/29/100
3

## Slide 107: Cash Flow Example: Solver Model
Notes: 11/29/100
3

## Slide 108: Material Management Issues
When to order materials? How much to order?
Example:
• Single material needed for Task B (2 units) and Task E (30 units)
• Fixed cost to place order = S
• Cost of holding raw materials proportional to number of unit-weeks in stock
• Cost of holding finished product greater than the cost of holding raw materials
• Project can be delayed (beyond 17 weeks) at cost of $P per week
Notes: 11/29/100
5

## Slide 109: Material Management Example
Task A
4 wks
Task B
8 wks
Task C
5 wks
Task D
6 wks
Task E
2 wks
Task F
3 wks
End
Start
2 units
30 units
Notes: 11/29/100
3

## Slide 110: Lot-Sizing Decisions in Projects
• To minimize holding costs, only place orders at Late Starting Times
• Can never reduce holding costs by delaying project
Time
1 2 3 4 5 6 7 8 9 10 11 12
Demand: 2 30
Order option #1: 32
Order option #2: 2 30
Choose the option that minimizes inventory cost = order cost + holding cost of raw materials
Notes: 11/29/100
3

## Slide 111
Time-Cost Tradeoffs

## Slide 112: Time-Cost Tradeoff Example

## Slide 113: Time-Cost Tradeoff Example (cont’d)
Project
Duration
(weeks)
Critical Path(s)
Task(s) Reduced
Total Direct
Cost
22
Start-A-C-End
-
$320
21
Start-A-C-End
A
$328
Start-A-B-End
20
Start-A-C-End
C
$338
Start-A-B-End
19
Start-A-C-End
C
$348
Start-A-B-End
18
Start-A-C-End
A, B
$361
Start-A-B-End

## Slide 114: Linear Time-Cost Tradeoff
In theory, the normal or expected duration of a task can be reduced by assigning additional resources to the task
Time
Cost
Crash Point
Normal Point
Slope (bj) = Increase in cost by reducing task by one time unit
Normal time =
Crash time =
Normal cost =
Crash cost =
Notes: 11/29/100
5

## Slide 115: Balancing Overhead & Direct Costs
Project Duration
Cost
Indirect (overhead) Costs
Direct Costs
Total Cost
Crash Time
Normal Time
Minimum Cost Solution
Notes: 11/29/100
5

## Slide 116: Time-Cost Tradeoff (Direct Costs Only)
Given Normal point with cost and time
and Crash point with cost and time
Assume constant marginal cost of crashing task j =
Decision Variables: Sj = Starting time of task j
END = End time of project
tj = Duration of task j
Minimize Total Direct Cost =
Sj ≥ Si + ti for all tasks i  Pj
for all tasks in project
END = Tmax
tj, Sj ≥ 0
Notes: 11/29/100
3

## Slide 117: General Time-Cost Tradeoffs
where
I = indirect (overhead) cost/time period
P = penalty cost/time period if END is delayed beyond deadline Tmax
L = number of time periods project is delayed beyond deadline Tmax
Minimize Total Costs = + I (END) + P L
QUESTION: HOW TO DEFINE L?
Notes: 11/29/100
3

## Slide 118: Software Project Schedules
“Observe that for the programmer, as for the chef, the urgency of the patron may govern the scheduled completion of the task, but it cannot govern the actual completion. An omelet, promised in ten minutes, may appear to be progressing nicely. But when it has not set in ten minutes, the customer has two choices--wait or eat it raw. Software customers have the same choices. The cook has another choice; he can turn up the heat. The result is often an omelet nothing can save--burned in one part, raw in another.”
F.P. Brooks, “The Mythical Man-Month”, Datamation, Vol 20, No 12 (Dec, 1974), pp. 44-52.
Notes: 11/29/100
3

## Slide 119: Coordination Costs (Software Development Project)
Assume you want to develop program that will require (approximately) 50,000 lines of PERL code
A typical programmer can write approximately 1500 lines of code per week
Coordination time is M (M-1)/2 weeks

## Slide 120: Brook’s Law
“Adding manpower to a late software project makes it later.”
F.P. Brooks, “The Mythical Man-Month”, Datamation, Vol 20, No 12 (Dec, 1974), pp. 44-52.
Notes: 11/29/100
3

## Slide 121: Compressing New Product Development Projects
Traditional Method
Design follows a sequential pattern where information about the new product is slowly accumulated in consecutive stages
Stage 0
Stage 1
Stage N

## Slide 122: New Product Development Process
Overlapped Product Design
Allows downstream design stages to start before preceding upstream stages have finalized their specifications….
Stage 0
Stage 1
Stage N

## Slide 123: Issues and Tradeoffs
What are the tradeoffs when moving from a traditional sequential product design process to an overlapped product design process?
• Increased uncertainty (that leads to additional work)
• Can add additional resources to tasks to reduce duration--but costs are increased

## Slide 124: Classic PERT Model Defined
• Since task durations are now random variables, time of any milestone (e.g., end of project) is now RV
• Assume all tasks are statistically independent
• Use values of j to identify expected critical path
• Since time of event (e.g., ESk) is now sum of independent RV’s, central limit theorem specifies that ESk is approximately normally distributed with mean E[ESk] and variance Var[ESk]
where there exists s paths to task k

## Slide 125: Classic PERT Model (cont’d)
Thus, expected project duration is defined as:
Using central limit theorem and standard normal distribution:

## Slide 126: PERT Example #1

## Slide 127: PERT Example #1 (cont’d)

## Slide 128: PERT Example #2
Task B

B
= 12

B
2
= 4
Task D

D
= 3

D
2
= 1
Task A

A
= 4

A
2
= 2
Task C

C
= 10

C
2
= 5
END
START

## Slide 129: Example #3: Discrete Probabilities

## Slide 130: Example #3 (cont’d)

## Slide 131: Example #3 (cont’d)
Criticality Indices
Expected Project Duration = 23.22

## Slide 132: Monte-Carlo Simulation (PERT Example 1)

## Slide 133: Calculating Confidence Intervals
For a confidence interval, we can use the sample mean and the estimated standard error of the mean where s is the sample standard deviation and n is the number of trials
Using a normal approximation, a (1- ) two-sided confidence interval is given by

## Slide 134: New Product Development Projects
Notes: 11/29/100
3

## Slide 135: New Product Development Projects (cont’d)
Notes: 11/29/100
3

## Slide 136: Critical Chain and the Theory of Constraints (TOC)
• Use deterministic CPM model with buffers to deal with any uncertainties,
• Place project buffer after last task to protect the customer’s completion schedule,
• Exploit constraining resources (make certain that resources are fully utilized),
• Avoid wasting time slack time by encouraging early task completions,
• Carefully monitor the status of the buffer(s) and communicate this status to other project team members on a regular basis, and
• Make certain that the project team is 100 percent focused on critical chain tasks
Project “Goal” (according to Goldratt): Meet Project Due Date
Notes: 11/29/100
3

## Slide 137: Project Buffer Defined
• Project Buffer is placed at the end of the project to protect the customer’s promised due date
PERT Example #1 Revisited with Project Buffer
Start
Task B
Programming
User
Task D
User
training
Task E
Implementation
End
Project
Buffer
Task A
requirements
analysis
Task C
Hardware
acquisition
Task F
Testing
Notes: 11/29/100
3

## Slide 138: Calculating Project Buffer Size
For tasks k on critical chain, we can calculate project buffer using following formula that project will be completed within worst-case duration estimates around 90 percent of the time:
For those “who want a scientific approach to sizing buffers....”

## Slide 139: Implications of Project Uncertainty
Assume that the duration of both tasks A and B are described by a normal distribution with a mean of 30 days
START
END
Task A
Task B
What is the probability that the project will be completed within 30 days?

## Slide 140: Uncertainty and Worker Behavior
Consider a project with two tasks that must be completed serially
The duration of each task is described by a RV with values Ti (i = 1, 2)
Start
Task 1
Task 2
End

## Slide 141: Parkinson’s Law (Expanding Work)
“Work expands so as to fill the time available for its completion”
Professor C.N. Parkinson (1957)
Set a deadline D = 24 days
So T(D) = project makespan (function of D) where
E[T(D)] = E(T1) + E(T2) + E[max(0, D - T1 - T2)]
E[T(D)] = 25 days

## Slide 142: Procrastinating Worker
Set a deadline D = 24 days
E’[T(D)] = E(T1) + E(T2) + E{max[0, D - T1 - E(T2)]}
Can show that E[T(D)] ≥ E’[T(D)] ≥ D
What are the implications for project managers?

## Slide 143: Schoenberger’s Hypothesis
An increase in the variability of task durations will increase the expected project duration….

## Slide 144: Schoenberger’s Hypothesis Illustrated

## Slide 145: Schoenberger’s Hypothesis Illustrated
Increasing the variance of Task A:
Results in an increased expected duration = 14.65 days
Expected duration equals 14.55 days

## Slide 146: Risk Management
• All projects involve some degree of risk
• Need to identify all possible risks and outcomes
• Need to identify person(s) responsible for managing project risks
• Identify actions to reduce likelihood that adverse events will occur

## Slide 147: Risk Analysis
Risk Exposure (RE) or Risk Impact =
(Probability of unexpected loss) x (size of loss)
Example: Additional features required by client
Loss: 3 weeks
Probability: 20 percent
Risk Exposure = (.20) (3 weeks) = .6 week

## Slide 148: How to Manage Project Risks?
Preventive Actions
• Actions taken in anticipation of adverse events
• May require action before project actually begins
• Examples?
Contingency Planning
• What will you do if an adverse event does occur?
• “Trigger point” invokes contingency plan
• Frequently requires additional costs

## Slide 149: Risk and Contracts

## Slide 150: Tornado Diagram

## Slide 151: Sensitivity Chart

## Slide 152: Van Allen Company

## Slide 153: Resource Allocation & Leveling
Resource Leveling: Reschedule the noncritical tasks to smooth resource requirements
Resource Allocation: Minimize project duration to meet resource availability constraints
Notes: 11/29/100
3

## Slide 154: Resource Allocation & Leveling
Three types of resources:
1) Renewable resources: “renew” themselves at the beginning of each time period (e.g., workers)
2) Non-Renewable resources: can be used at any rate but constraint on total number available
3) Doubly constrained resources: both renewable and non-renewable
Notes: 11/29/100
3

## Slide 155: Resource Leveling
Notes: 11/29/100
3

## Slide 156: Resource Leveling: Early Start Schedule
Notes: 11/29/100
3

## Slide 157: Resource Leveling: Late Start Schedule
Notes: 11/29/100
3

## Slide 158: Resource Leveling: Microsoft Project
Notes: 11/29/100
3

## Slide 159: Renewable Resource Allocation Example (Single Resource Type)
Ta
sk
B
3
w
k
s
Ta
sk
D
5
w
ks
Ta
sk
A
4
w
k
s
Ta
sk
E
4
w
k
s
START
END
Ta
sk
C
1
w
k
3 workers
5 workers
6 workers
8 workers
7 workers
Maximum number of workers available = R = 9 workers
Notes: 11/29/100
3

## Slide 160: Resource Allocation Example: Early Start Schedule
Maximum number of workers available = R = 9 workers
Notes: 11/29/100
3

## Slide 161: Resource Allocation Example: Late Start Schedule
Maximum number of workers available = R = 9 workers
Notes: 11/29/100
3

## Slide 162: Resource Allocation Heuristics
Some heuristics for assigning priorities to available tasks j, where denotes the number of units of resource k used by task j
1) FCFS: Choose first available task
2) GRU: (Greatest) resource utilization =
3) GRD: (Greatest) resource utilization x task duration =
4) ROT: (Greatest) resource utilization/task duration =
5) MTS: (Greatest) number of total successors
6) SPT: Shortest processing time = min {tj}
7) MINSLK: Minimum (total) slack
8) LFS: Minimum (total) slack per successor
9) ACTIMj: (Greatest) time from start of task j to end of project = CP - LSj
10) ACTRESj: (max) (ACTIMj)
11) GENRESj: w ACTIMj + (1-w) ACTRESj where 0 ≤ w ≤ 1

## Slide 163: Resource Allocation Problem #2
Notes: 11/29/100
3

## Slide 164: How to schedule tasks to minimize project makespan?
Priority scheme: schedule tasks using total slack (i.e., tasks with smaller total slack have higher priority)
Notes: 11/29/100
3

## Slide 165: Resource Allocation Example (cont’d)
But, can we do better? Is there a better priority scheme?
Notes: 11/29/100
3

## Slide 166: Microsoft Project Solution (Resource Leveling Option)
Solution by: Microsoft Project 2000
Notes: 11/29/100
3

## Slide 167: Critical Chain Project Management
• Identify the critical chain: set of tasks that determine the overall duration of the project
• Use deterministic CPM model with buffers to deal with uncertainty
• Remove padding from activity estimates (otherwise, slack will be wasted). Estimate task durations at median.
• Place project buffer after last task to protect customer’s completion schedule
• Exploit constraining resource(s)
• Avoid wasting slack times by encouraging early task completions
• Have project team focus 100% effort on critical tasks
• Work to your plan and avoid tampering
• Carefully monitor and communicate buffer status

## Slide 168: Critical Chain Buffers
Project Buffer: placed after last task in project to protect schedule
Feeding Buffers: placed between a noncritical task and a critical task when the noncritical task is an immediate predecessor of the critical task
Resource Buffers: placed just before a critical task that uses a new resource type
Notes: 11/29/100
3

## Slide 169: Critical Chain Illustrated
Resource Buffers
Feeding Buffers
Notes: 11/29/100
3

## Slide 170: Non-Renewable Resources
Notes: 11/29/100
3

## Slide 171: Non-Renewable Resources: Graphical Solution
Notes: 11/29/100
3

## Slide 172: Resource Allocation Problem #3
Issue: When is it better to “team” two or more workers versus letting them work separately?
• Have 2 workers, Bob and Barb, and 4 tasks: A, B, C, D
• Bob and Barb can work as a team, or they can work separately
• When should workers be assigned to tasks? Which configuration do you prefer?

## Slide 173: How to Assign Project Teams?
Configuration #1
Bob and Barb work jointly on all four tasks; assume that they can complete each task in one-half the time needed if either did the tasks individually
A
C
B
D
Start
End
Configuration #2
Bob and Barb work independently. Bob is assigned to tasks A and C; Barb is assigned to tasks B and D

## Slide 174: Bob and Barb: Configuration #1
Configuration #1
Bob and Barb work jointly on all four tasks.
What is the expected project makespan?

## Slide 175: Bob and Barb: Configuration #2
Bob and Barb work independently. Bob is assigned to tasks A and C; Barb is assigned to tasks B and D

## Slide 176: Bob and Barb: Configuration #2
Bob and Barb work independently. Bob is assigned to tasks A and C; Barb is assigned to tasks B and D
Expected Project Makespan: 16.42

## Slide 177: Parallel Tasks with Random Durations
START
END
Task B
Task A
• Assume that both Tasks A and B have possible durations:
8 days with probability = 0.5
10 days with probability = 0.5
• What is expected duration of project? (Is it 9 days?)

## Slide 178: Project Monitoring and Control
“It is of the highest importance in the art of detection to be able to recognize, out of a number of acts, which are incidental and which are vital. Otherwise your energy and attention must be dissipated instead of being concentrated.”
  Sherlock Holmes

## Slide 179: Status Reporting?
One day my Boss asked me to submit a status report to him concerning a project I was working on. I asked him if tomorrow would be soon enough. He said, "If I wanted it tomorrow, I would have waited until tomorrow to ask for it!"
New business manager, Hallmark Greeting Cards

## Slide 180: Control System Issues
What are appropriate performance metrics?
What data should be used to estimate the value of each performance metric?
How should data be collected? From which sources? At what frequency?
How should data be analyzed to detect current and future deviations?
How should results of the analysis be reported? To whom? How often?

## Slide 181: Controlling Project Risks
Key issues to control risk during projecct:
(1) what is optimal review frequency, and
(2) what are appropriate review acceptance levels at each stage?
“Both over-managed and under-managed development processes result in lengthy design lead time and high development costs.”
Ahmadi & Wang. “Managing Development Risk in Product Design Processes”, 1999

## Slide 182: Project Control & System Variation
Common cause variation: “in-control” or normal variation
Special cause variation: variation caused by forces that are outside of the system
According to Deming:
• Treating common cause variation as if it were special cause variation
is called “tampering”
• Tampering always degrades the performance of a system

## Slide 183: Control System Example #1
Project plan: We estimate that a task will take 4 weeks and require
1600 worker-hours
At the end of Week 1, 420 worker-hours have been used
Is the task “out of control”?

## Slide 184: Control System Example (cont’d)
Week 2: Task expenses = 460 worker-hours
Is the task “out of control”?

## Slide 185: Control System Example (cont’d)
Week 3: Task expenses = 500 worker-hrs
Is the task “out of control”?

## Slide 186: Earned Value Analysis
• Integrates cost, schedule, and work performed
• Based on three metrics that are used as the basic building blocks:
BCWS: Budgeted cost of work scheduled
ACWP: Actual cost of work performed
BCWP: Budgeted cost of work performed

## Slide 187: Schedule Variance (SV)
Schedule Variance (SV) = difference between value of work completed and value of scheduled work
Schedule Variance (SV) = Earned Value - Planned Value
= BCWP - BCWS

## Slide 188: Cost Variance (CV)
Cost Variance (CV) = difference between value of work completed and actual expenditures
Cost Variance (CV) = Earned Value - Actual Cost
= BCWP - ACWP

## Slide 189: Earned Values Metrics Illustrated
Worker-Hours
Week 1
Week 2
Week 3
Week 4
Week 5
Week 6
Present time
BAC
Actual Cost (ACWP)
Earned Value (BCWP)
Planned Value (BCWS)
Schedule Variance (SV)
Cost Variance (CV)

## Slide 190: Relative Measure: Schedule Index
If SI = 1, then task is on schedule
If SI > 1, then task is ahead of schedule
If SI < 1, then task is behind schedule

## Slide 191: Relative Measure: Cost Index
If CI = 1, then work completed equals payments (actual expenditures)
If CI > 1, then work completed is ahead of payments
If CI < 1, then work completed is behind payments (cost overrun)

## Slide 192: Example #2

## Slide 193: Example #2 (cont’d)
Progress report at the end of week #5:
Cumulative Percent of Work Completed:
Worker-Hours Charged to Project:

## Slide 194: Example #2 (cont’d)
Progress report at the end of week #5:

## Slide 195: Example #2 (cont’d)

## Slide 196: Using a Fixed 20/80 Rule
Cumulative Percent of Work Completed:

## Slide 197: Using a Fixed 20/80 Rule

## Slide 198: Updating Forecasts: Pessimistic Viewpoint
= (64/52.2) 128 = 1.23 x 128 = 156.94 worker-hrs
Assumes that rate of cost overrun will continue for life of project….

## Slide 199: Updating Forecasts: Optimistic Viewpoint
Assumes that cost overrun experienced to date will cease and no further cost overruns will be experienced for remainder of project life…

## Slide 200: Multi-tasking with Multiple Projects
Project A
Project B
A-1
B-1
A-2
B-2
A-3
A-4
B-3
B-4
Consider two projects with and without multi-tasking
How to prioritize your work when you have multiple
projects and goals?
Notes: 11/29/100
5

## Slide 201: Due-Date Assignment with Dynamic Multiple Projects
• Projects arrive dynamically (common situation for both manufacturing and service organizations)
• How to set completion (promise) date for new projects?
• Firms may have complete control over due-dates or only partial control (i.e., some due dates are set by external sources)
• How to allocate resources among competing projects and tasks (so that due dates can be realized)?
• What are appropriate metrics for evaluating various rules?
Notes: 11/29/100
5

## Slide 202: What Does the Research Tell Us?
• Study by Dumond and Mabert* investigated four due date assignment rules and five scheduling heuristics
• Simulated 250 projects that randomly arrive over 2000 days
• average interarrival time = 8 days
• 6 - 49 tasks per project (average = 24); 1 - 3 resource types
• average critical path = 31.4 days (range from 8 to 78 days)
• Performance criteria: 1) mean completion time
2) mean project lateness
3) standard deviation of lateness
4) total tardiness of all projects
• Partial and complete control on setting due dates
* Dumond, J. and V. Mabert. “Evaluating Project Scheduling and Due Date Assignment Procedures: An Experimental Analysis” Management Science, Vol 34, No 1 (1988), pp 101-118.
Notes: 11/29/100
5

## Slide 203: Experimental Results
• No one scheduling heuristic performs best across all due date setting combinations
• Mean completion times for all scheduling and due date rules not significantly different
• FCFS scheduling rules increase total tardiness
• SPT-related rules do not work well in PM (SASP)
• Best to use more detailed information to establish due dates
Notes: 11/29/100
5

## Slide 204: Project Management Maturity Models
• Methodologies to assess your organization’s current level of PM capabilities
• Based on extensive empirical research that defines “best practice” database as well as plan for improving PM process
• Process of improvement describes the PM process from “ineffective” to “optimized”
• Also known as “Capability Maturity Models”
Notes: 11/29/100
5

## Slide 205: PM Maturity Model Example*
Ad-Hoc The project management process is described as disorganized, and occasionally even chaotic. Systems and processes are not defined. Project success depends on individual effort. Chronic cost and schedule problems.
Abbreviated: Some project management processes are established to track cost, schedule, and performance. Underlying disciplines, however, are not well understood or consistently followed. Project success is largely unpredictable and cost and schedule problems are the norm.
Organized: Project management processes and systems are documented, standardized, and integrated into an end-to-end process for the company. Project success is more predictable. Cost and schedule performance is improved.
4) Managed: Detailed measures of the effectiveness of project management are collected and used by management. The process is understood and controlled. Project success is more uniform. Cost and schedule performance conforms to plan.
5) Adaptive: Continuous improvement of the project management process is enabled by feedback from the process and from piloting innovative ideas and technologies. Project success is the norm. Cost and schedule performance is continuously improving.
* source: The Project Management Institute PM Network (July, 1997), Micro Frame Technologies, Inc. and Project Management Technologies, Inc. (http://pm32.hypermart.net/)
Notes: 11/29/100
5