## Cash Flow Exple
0
0
| Annual discount rate = |  | 20%
Monthly discount rate = |  |  | 1.667%
Activity | Duration (mos) | Start Time | Finish Time | Cash Flow | Dollar-Months | NPV
START* | 0 | 0 | 0 | -
Task A | 2 | 0 | 2 | -
Task B | 8 | 0 | 8 | -
M 1* | 0 | 3 |  | -5000 | -15000 | -4758.1075
Task C | 4 | 3.75 | 7.75 | -
M 2* | 0 | 8 |  | 3000 | 24000 | 2628.4068
Task D | 8 | 3 | 11 | -
Task E | 3 | 8 | 11 | -
END* | 0 | 11 | 11 | 3000 | 33000 | 2501.2484
[5 empty] | 42000 | 371.5477
*denotes milestone
Note on C10: Start of project (set equal to zero)
Note on C11: STARTA = denotes the starting time of task A
Note on C13: SM1denotes the occurrence time of milestone M1
Note on C15: SM2 denotes the occurrence time of milestone M2
M1
END
START
Task B
8 mos
Receive payment of $3000
Receive payment of $3000
Make payment of $5000
Task C
4 mos
Task A
2 mos
M2
Task D
8 mos
Task E
3 mos