## Simulation-beta
Monte-Carlo Simulation Illustrated
Beta Distribution
Duration Estimates
Task | Description | Predecessors | Optimistic | Pessimistic | Likely | Random (1) | Random (2) | Random (3) | Random (4) | TR1 | X1 | Random (1) | Random (2) | TR2 | X2 | X
A | Requirements Analysis | none | 2 | 14 | 6 | 0.065989 | 0.53475 | 0.4234 | 0.031424 | 0.00046951 | 0.83209 | 0.7908 | 0.35693 | 0.28226 | 0.27467 | 0.75182
B | Programming | A | 4 | 12 | 7 | 0.38369 | 0.13134 | 0.11478 | 0.73283 | 0.0042388 | 0.59319 | 0.29444 | 0.53953 | 0.15886 | 0.39949 | 0.59756
C | Hardware acquisition | A | 2 | 13 | 8 | 0.28779 | 0.45876 | 0.14562 | 0.3836 | 0.0073748 | 0.53306 | 0.30605 | 0.48469 | 0.14834 | 0.41437 | 0.56264
D | User training | A | 12 | 18 | 14 | 0.43566 | 0.19991 | 0.95919 | 0.93754 | 0.078318 | 0.27653 | 0.70191 | 0.47252 | 0.33167 | 0.23965 | 0.53573
E | Implementation | B, C | 3 | 7 | 5 | 0.89703 | 0.99228 | 0.09372 | 0.0012727 | 0.00010617 | 0.9935 | 0.83161 | 0.59344 | 0.49351 | 0.15335 | 0.86628
F | Testing | E | 3 | 7 | 4 | 0.5551 | 0.70058 | 0.98918 | 0.73104 | 0.28122 | 0.13774 | 0.79934 | 0.65652 | 0.52478 | 0.14001 | 0.49591
END | End of project | D, F | 0 | 0 | 0 | 0.067189 | 0.44517 | 0.89204 | 0.28091 | 0.0074952 | 0.5313 | 0.69789 | 0.57541 | 0.40157 | 0.19812 | 0.72839
| Task Duration | Early | Latest | Total | Expected
Task | (Beta Distribution) | Start | Finish | Slack | Duration | Variance
A | 11.0219 | 0 | 11.0219 | 0 | 6.6667 | 4
B | 8.7805 | 11.0219 | 19.8024 | 0 | 7.3333 | 1.7778
C | 8.189 | 11.0219 | 19.8024 | 0.59148 | 7.8333 | 3.3611
D | 15.2144 | 11.0219 | 31.2512 | 5.0149 | 14.3333 | 1
E | 6.4651 | 19.8024 | 26.2675 | 0 | 5 | 0.44444
F | 4.9836 | 26.2675 | 31.2512 | 0 | 4.3333 | 0.44444
END | 0 | 31.2512 | 31.2512 | 0 | 0 | 0
| PERT Expected Duration = | 23.8333 |  | Expected CP = | {A, C, E, F, END}
| PERT Variance = | 8.25
Run | Project Duration | t(B) | t(C) | t(D) | t(E) | t(F)
1 | 31.2512 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
2 | 29.9674 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
3 | 25.3718 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
4 | 30.8651 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
5 | 35.2626 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
6 | 29.3115 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
7 | 31.2661 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
8 | 27.2429 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
9 | 31.6461 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
10 | 30.9948 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
11 | 30.5032 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
12 | 33.6674 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
13 | 26.3743 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
14 | 26.8387 | 0 | 0 | 1 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
15 | 25.2848 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
16 | 28.2563 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
17 | 32.5075 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
18 | 24.8902 | 0 | 0 | 1 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
19 | 31.917 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
20 | 31.1428 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
21 | 26.8376 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
22 | 20.9734 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
23 | 25.6456 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
24 | 24.7623 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
25 | 32.5127 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
26 | 18.5506 | 0 | 0 | 1 | 0 | 0 | [10 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
27 | 25.2755 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
28 | 20.2981 | 0 | 0 | 1 | 0 | 0 | [10 empty] | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
29 | 25.8645 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
30 | 29.355 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
31 | 32.2195 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
32 | 32.4841 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
33 | 33.7312 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
34 | 26.4359 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
35 | 29.1808 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
36 | 28.508 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
37 | 35.0917 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
38 | 27.9187 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
39 | 36.0033 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
40 | 22.3441 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
41 | 23.4099 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
42 | 30.2192 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
43 | 23.417 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
44 | 33.7938 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
45 | 34.3471 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
46 | 21.0409 | 0 | 0 | 1 | 0 | 0 | [10 empty] | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
47 | 30.0353 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
48 | 26.7194 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
49 | 27.4596 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
50 | 24.4393 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
51 | 25.289 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
52 | 17.8939 | 0 | 0 | 1 | 0 | 0 | [10 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
53 | 25.0824 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
54 | 31.5014 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
55 | 25.1076 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
56 | 31.3366 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
57 | 33.5192 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
58 | 18.8344 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
59 | 20.9679 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
60 | 36.0951 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 32.8249 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
62 | 35.9731 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
63 | 29.9377 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
64 | 31.2135 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
65 | 27.1698 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
66 | 27.001 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
67 | 27.9064 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
68 | 25.6924 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
69 | 34.1467 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
70 | 31.5552 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
71 | 21.7506 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
72 | 31.7526 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
73 | 27.9907 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
74 | 22.5312 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
75 | 30.3409 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
76 | 28.81 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
77 | 29.1649 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
78 | 29.2876 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
79 | 30.0449 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
80 | 23.1773 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
81 | 25.3656 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
82 | 35.6961 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
83 | 23.997 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
84 | 26.433 | 0 | 0 | 1 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
85 | 27.8921 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
86 | 26.9338 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
87 | 28.6828 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
88 | 34.8698 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
89 | 24.475 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
90 | 32.7195 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
91 | 25.8808 | 0 | 0 | 1 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
92 | 31.7535 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
93 | 23.5833 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
94 | 29.9572 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
95 | 31.1778 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
96 | 25.8501 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
97 | 25.9574 | 0 | 0 | 1 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
98 | 29.1578 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
99 | 35.4458 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
100 | 22.2705 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
101 | 28.5839 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
102 | 23.0731 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
103 | 28.9966 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
104 | 26.5738 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
105 | 23.7118 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
106 | 29.4064 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
107 | 23.6712 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
108 | 29.9079 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
109 | 26.9703 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
110 | 33.3387 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
111 | 26.1261 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
112 | 33.4341 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
113 | 25.1794 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
114 | 32.7626 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
115 | 27.71 | 0 | 0 | 1 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
116 | 18.6347 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
117 | 30.2091 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
118 | 26.1472 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
119 | 33.4344 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
120 | 28.3937 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
121 | 25.6295 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
122 | 29.6551 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
123 | 21.6115 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
124 | 33.6244 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
125 | 29.9145 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
126 | 29.5585 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
127 | 20.2681 | 0 | 0 | 1 | 0 | 0 | [10 empty] | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
128 | 27.0253 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
129 | 25.3169 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
130 | 17.5911 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
131 | 27.4304 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
132 | 27.7625 | 0 | 0 | 1 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
133 | 19.8709 | 0 | 0 | 1 | 0 | 0 | [10 empty] | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
134 | 21.0018 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
135 | 25.7879 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
136 | 34.6032 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
137 | 23.7801 | 0 | 0 | 1 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
138 | 23.0935 | 0 | 0 | 1 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
139 | 23.8316 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
140 | 29.8835 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
141 | 29.1512 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
142 | 22.6909 | 0 | 0 | 1 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
143 | 27.1305 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
144 | 29.6655 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
145 | 29.1421 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
146 | 32.1413 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
147 | 20.392 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
148 | 32.1974 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
149 | 30.7759 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
150 | 25.1891 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
151 | 28.7551 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
152 | 25.1469 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
153 | 35.6243 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
154 | 26.3825 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
155 | 30.6262 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
156 | 30.7792 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
157 | 23.9307 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
158 | 32.5119 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
159 | 26.7866 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
160 | 22.6914 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
161 | 24.7858 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
162 | 20.5027 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
163 | 28.0632 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
164 | 29.6028 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
165 | 25.2453 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
166 | 25.0651 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
167 | 31.7211 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
168 | 34.8703 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
169 | 30.4426 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
170 | 26.2943 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
171 | 25.7013 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
172 | 22.7988 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
173 | 26.796 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
174 | 25.3228 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
175 | 24.9776 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
176 | 30.8945 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
177 | 27.8703 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
178 | 23.1772 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
179 | 26.5464 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
180 | 31.4102 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
181 | 23.3188 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
182 | 22.5335 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
183 | 26.3717 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
184 | 22.9298 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
185 | 31.0519 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
186 | 29.444 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
187 | 15.3887 | 0 | 0 | 1 | 0 | 0 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
188 | 24.0865 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
189 | 29.9361 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
190 | 22.0198 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
191 | 18.2333 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
192 | 28.3807 | 0 | 0 | 1 | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
193 | 26.4002 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
194 | 28.5741 | 1 | 0 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
195 | 31.763 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
196 | 27.2163 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
197 | 28.627 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
198 | 24.9396 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
199 | 27.4525 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
200 | 31.1825 | 0 | 1 | 0 | 1 | 1 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
Ave | 27.6629 | 51% | 40% | 9% | 91% | 91%
Var | 18.0729
| Project Makespan | Lower Limit | Upper Limit
| 95% Confidence interval | 27.0737 | 28.2521
| 99% Confidence interval | 26.8889 | 28.437
36.0951 | Project Makespan | Range | Cum Freq | Freq
15.3887 |  | 15.3887 | 1 | 1
|  | 17.4593 | 7 | 6
2.0706 |  | 19.5299 | 16 | 9
|  | 21.6006 | 36 | 20
|  | 23.6712 | 67 | 31
|  | 25.7419 | 101 | 34
|  | 27.8125 | 132 | 31
|  | 29.8832 | 169 | 37
|  | 31.9538 | 187 | 18
|  | 34.0244 | 199 | 12
36.0951

## Figure 6.10
Monte-Carlo Simulation Illustrated
Uniform Distribution
Duration Estimates
Task | Description | Predecessors | Optimistic | Pessimistic | L䁩kely | Random #
A | Requirements Analysis | none | 2 | 14 | 6 | 0.75437
B | Programming | A | 4 | 12 | 7 | 0.65255
C | Hardware acquisition | A | 2 | 13 | 8 | 0.88939
D | User training | A | 12 | 18 | 14 | 0.7412
E | Implementation | B, C | 3 | 7 | 5 | 0.92129
F | Testing | E | 3 | 7 | 4 | 0.58254
END | End of project | D, F | 0 | 0 | 0 | 0.78451
| Task Duration | Early | Latest | Total | Expected
Task | (Uniform Dist) | Start | Finish | Slack | Duration | Variance
A | 11.0525 | 0 | 11.0525 | 0 | 6.6667 | 4
B | 9.2204 | 11.0525 | 22.8358 | 2.5629 | 7.3333 | 1.7778
C | 11.7833 | 11.0525 | 22.8358 | 0 | 7.8333 | 3.3611
D | 16.4472 | 11.0525 | 34.8511 | 7.3515 | 14.3333 | 1
E | 6.6852 | 22.8358 | 29.521 | 0 | 5 | 0.44444
F | 5.3301 | 29.521 | 34.8511 | 0 | 4.3333 | 0.44444
END | 0 | 34.8511 | 34.8511 | 0 | 0 | 0
| PERT Expected Duration = | 23.8333 |  | Expected CP = | {A, C, E, F, END}
| PERT Variance = | 8.25
Run | Project Duration | t(B) | t(C) | t(D) | t(E) | t(F)
1 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
147 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
152 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
153 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
154 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
163 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
164 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
166 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
167 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
168 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
172 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
173 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
174 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
175 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
176 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
182 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
183 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
184 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
187 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
188 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
189 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
191 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
193 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
194 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
195 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
196 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
197 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
198 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
199 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | 34.8511 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ave | 34.8511 | 0% | 100% | 0% | 100% | 100%
Var | 0
| Project Makespan | Lower Limit | Upper Limit
| 95% Confidence interval | 34.8511 | 34.8511
| 99% Confidence interval | 34.8511 | 34.8511
34.8511 | Project Makespan | Range | Cum Freq | Freq
34.8511 |  | 34.8511 | 0 | 0
|  | 34.8511 | 0 | 0
0 |  | 34.8511 | 0 | 0
|  | 34.8511 | 0 | 0
|  | 34.8511 | 0 | 0
|  | 34.8511 | 0 | 0
|  | 34.8511 | 0 | 0
|  | 34.8511 | 0 | 0
|  | 34.8511 | 0 | 0
|  | 34.8511 | 0 | 0
34.8511

## Buffer
Critical Task | Description | Pessimistic time estimate, tp | Expected duration m | tp - m | (tp - m)2
A | Requirements analysis | 14 | 6.67 | 7.33 | 53.7289
C | Hardware acquisition | 13 | 7.83 | 5.17 | 26.7289
E | Implementation | 7 | 5 | 2 | 4
F | Testing | 7 | 4.33 | 2.67 | 7.1289
[5 empty] | 91.5867 | 9.5701
Start
Task B
Programming
User
Task D
uwer
training
Task E
Implementation
End
Project
Buffer
Task A
requirements
analysis
Task C
hardware
acquiition
Task F
testing
Project Buffer

## Figure 6.1
Classic PERT Example #1
|  |  |  | Duration Estimates |  | Expected |  | Buffer
Task | Description | Predecessors | Optimistic | Pessimistic | L䁩kely | Duration | Variance | Calculations
A | Requirements Analysis | none | 2 | 14 | 6 | 6.6667 | 4 | 53.7778
B | Programming | A | 4 | 12 | 7 | 7.3333 | 1.7778
C | Hardware acquisition | A | 2 | 13 | 8 | 7.8333 | 3.3611 | 26.6944
D | User training | A | 12 | 18 | 14 | 14.3333 | 1
E | Implementation | B, C | 3 | 7 | 5 | 5 | 0.44444 | 4
F | Testing | E | 3 | 7 | 4 | 4.3333 | 0.44444 | 7.1111
END | End of project | D, F | 0 | 0 | 0 | 0 | 0
Expected
Task | Path | Early Start | Variance | Due Date | Zi | Pr(zi)
| Start-A | 6.6667 | 4 | 6 | -0.33333 | 36.94%
| Start-A-C | 14.5 | 7.3611 | 15 | 0.18429 | 57.31%
| Start-A-C-E | 19.5 | 7.8056 | 20 | 0.17896 | 57.1%
| Start-A-C-E-F-End | 23.8333 | 8.25 | 25 | 0.40618 | 65.77%
Classic PERT Results
| PERT Expected Duration = | 23.8333 | Expected CP | = {Start, A, C, E, F, End}
| PERT Variance = | 8.25