## Figure 5.11
| Task | Normal Duration | Normal Cost | Marginal Cost to Crash One Week
| A | 7 | 60 | 8
| B | 6 | 85 | 5
| C | 15 | 55 | 10
| D | 10 | 120 | 4
Decision variables:
STARTj = Starting time of task j
Task Starting Times |  | Duration (tj) |  | Task Finish Times |  | Normal |  | Crash
Variables | Values | Variables | Values | Variables | Values | Duration | Cost | Duration | Slope (bj)
START | 0 |  |  |  |  | 0 | 0 | 0 | -
STARTA | 0 | tA | 6 | FINISHA | 6 | 7 | 60 | 5 | 8
STARTB | 0 | tB | 6 | FINISHB | 6 | 6 | 85 | 4 | 5
STARTC | 6 | tC | 13 | FINISHC | 19 | 15 | 55 | 13 | 10
STARTD | 6.8706 | tD | 10 | FINISHD | 16.8706 | 10 | 120 | 8 | 4
END | 19 |  |  |  |  | 0 | 0 | 0 | -
Tmax | 18 | [5 empty] | 320
|  | Task A | Task B | Task C | Task D
| Direct Cost/Task= | 68 | 85 | 75 | 120
| Overhead Cost/wk = | 10
| Penalty cost/wk = | 0
| Total Direct Costs = | 348
| Overhead costs = | 190
| Penalty costs = | 0
| Total Cost = | 538
Note on C34: Starting time of project
Note on C35: Starting time of task A
Note on C36: Starting time of task B
Note on C37: Starting time of task C
Note on C38: Starting time of task D
Note on C39: Time of project END (Project Makespan)
Note on C40: Due date of project
Note on D43: Direct labor cost for task A
Note on D44: This is an input parameter
Note on D45: This is an input parameter
Note on E35: Duration of task A
Note on E36: Duration of task B
Note on E37: Duration of task C
Note on E38: Duration of task D
Note on G35: Completion time for task A
Note on G36: Completion time for task B
Note on G37: Completion time for task C
Note on G38: Completion time for task D
Note on I40: Total direct labor cost if all tasks are performed at their normal durations
Note on J35: Min duration for task A
Note on K33: Marginal cost of crashing one week
A
B
C
D
D
Start
End