## Budget
|  |  |  | 400 | 600 |  |  |  | Early Start Times
Task or Milestone | Duration (tj) | Early Start Time (ESj) | Latest Start Time (LSj) | No. of Resource A workers | No. of Resource B workers | Material Costs | Direct Labor Cost/wk | Labor + Materials | Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
START | 0 | 0 | 0 | - | - | - | - | - | A | 1140 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800
A | 14 | 0 | 0 | 2 | 0 | 340 | 800 | 1140 | B | 8925 | 8800 | 8800 | 8800 | 8800 | 8800 | 8800 | 8800 | 8800
B | 9 | 0 | 5 | 4 | 12 | 125 | 8800 | 8925 | C | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600
C | 20 | 0 | 9 | 3 | 14 | 0 | 9600 | 9600 | D | [13 empty] | 5000 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800
D | 12 | 14 | 14 | 0 | 8 | 200 | 4800 | 5000 | E | [25 empty] | 960 | 400 | 400 | 400 | 400 | 400
E | 6 | 26 | 29 | 1 | 0 | 560 | 400 | 960 | F | [25 empty] | 7690 | 7600 | 7600 | 7600 | 7600 | 7600 | 7600 | 7600 | 7600
F | 9 | 26 | 26 | 4 | 10 | 90 | 7600 | 7690 | Weekly Subtotals | 19665 | 19200 | 19200 | 19200 | 19200 | 19200 | 19200 | 19200 | 19200 | 10400 | 10400 | 10400 | 10400 | 15400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 4800 | 4800 | 4800 | 4800 | 4800 | 8650 | 8000 | 8000 | 8000 | 8000 | 8000 | 7600 | 7600 | 7600
END | 0 | 35 | 35 | - | - | - | - | - | Cumulative | 19665 | 38865 | 58065 | 77265 | 96465 | 115665 | 134865 | 154065 | 173265 | 183665 | 194065 | 204465 | 214865 | 230265 | 244665 | 259065 | 273465 | 287865 | 302265 | 316665 | 321465 | 326265 | 331065 | 335865 | 340665 | 349315 | 357315 | 365315 | 373315 | 381315 | 389315 | 396915 | 404515 | 412115
Late Start Times
[9 empty] | Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34
[9 empty] | A | 1140 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800 | 800
[9 empty] | B |  |  |  |  | 8925 | 8800 | 8800 | 8800 | 8800 | 8800 | 8800 | 8800 | 8800
[9 empty] | C | [8 empty] | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600 | 9600
[9 empty] | D | [13 empty] | 5000 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | 4800
[9 empty] | E | [28 empty] | 960 | 400 | 400 | 400 | 400 | 400
[9 empty] | F | [25 empty] | 7690 | 7600 | 7600 | 7600 | 7600 | 7600 | 7600 | 7600 | 7600
[9 empty] | Weekly Subtotals | 1140 | 800 | 800 | 800 | 9725 | 9600 | 9600 | 9600 | 19200 | 19200 | 19200 | 19200 | 19200 | 15400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 17290 | 17200 | 17200 | 8560 | 8000 | 8000 | 8000 | 8000 | 8000
[9 empty] | Cumulative | 1140 | 1940 | 2740 | 3540 | 13265 | 22865 | 32465 | 42065 | 61265 | 80465 | 99665 | 118865 | 138065 | 153465 | 167865 | 182265 | 196665 | 211065 | 225465 | 239865 | 254265 | 268665 | 283065 | 297465 | 311865 | 329155 | 346355 | 363555 | 372115 | 380115 | 388115 | 396115 | 404115 | 412115
[9 empty] | Early Start Schedule | 19665 | 38865 | 58065 | 77265 | 96465 | 115665 | 134865 | 154065 | 173265 | 183665 | 194065 | 204465 | 214865 | 230265 | 244665 | 259065 | 273465 | 287865 | 302265 | 316665 | 321465 | 326265 | 331065 | 335865 | 340665 | 349315 | 357315 | 365315 | 373315 | 381315 | 389315 | 396915 | 404515 | 412115
[9 empty] | Late Start Schedule | 1140 | 1940 | 2740 | 3540 | 13265 | 22865 | 32465 | 42065 | 61265 | 80465 | 99665 | 118865 | 138065 | 153465 | 167865 | 182265 | 196665 | 211065 | 225465 | 239865 | 254265 | 268665 | 283065 | 297465 | 311865 | 329155 | 346355 | 363555 | 372115 | 380115 | 388115 | 396115 | 404115 | 412115
[9 empty] | Early Start Schedule | 19665 | 19200 | 19200 | 19200 | 19200 | 19200 | 19200 | 19200 | 19200 | 10400 | 10400 | 10400 | 10400 | 15400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 4800 | 4800 | 4800 | 4800 | 4800 | 8650 | 8000 | 8000 | 8000 | 8000 | 8000 | 7600 | 7600 | 7600
[9 empty] | Late Start Schedule | 1140 | 800 | 800 | 800 | 9725 | 9600 | 9600 | 9600 | 19200 | 19200 | 19200 | 19200 | 19200 | 15400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 17290 | 17200 | 17200 | 8560 | 8000 | 8000 | 8000 | 8000 | 8000
Early Start Schedule Cumulative Cash Flows
Latest Start Schedule Cumulative Cash Flows
Region of Feasible Cumulative Cash Flows
Early Start Schedule
Late Start Schedule

## Figure 4.12
| Starting Times of Tasks (Milestones) |  |  | Ending Times of Tasks
Task (Milestone) | Variable | Value | Duration (wks) | Variable | Value
START | START | 0 | 0
Task A | STARTA | 0 | 14 | FINISHA | 14
Task B | STARTB | 0 | 9 | FINISHB | 9
Task C | STARTC | 0 | 20 | FINISHC | 20
Task D | STARTD | 14 | 12 | FINISHD | 26
Task E | STARTE | 26 | 6 | FINISHE | 32
Task F | STARTF | 26 | 9 | FINISHF | 35
END | END | 35 | 0
| Sum of task starting times = | 101
Note on C31: Starting time of project
Note on C32: Start time of task A
Note on C33: Start time of task B
Note on C40: Results in task starting times set equal to their earliest starting times

## Figures 4.10 & 4.11
|  | I M M E D I A T E |  | E A R L I E S T |  | L A T E S T
Task or Milestone | Duration ( ) | Predecessors ( ) | Successors ( ) | Start Time (ESi) | Finish Time | Start Time | Finish Time (LFi)
START | 0 | - | A, B, C | 0 | 0 | 0 | 0
A | 14 | START | D | 0 | 14 | 0 | 14
B | 9 | START | D | 0 | 9 | 5 | 14
C | 20 | START | E | 0 | 20 | 9 | 29
D | 12 | A, B | E, F | 14 | 26 | 14 | 26
E | 6 | C, D | END | 26 | 32 | 29 | 35
F | 9 | D | END | 26 | 35 | 26 | 35
END | 0 | E, F | - | 35 | 35 | 35 | 35
Task or Milestone | Duration ( ) | Earliest Start Time (ESi) | Lastest Finish Time (LFi) | Total Slack | Free Slack | Safety Slack | Independent Slack | Critical Task?
START | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Yes
A | 14 | 0 | 14 | 0 | 0 | 0 | 0 | Yes
B | 9 | 0 | 14 | 5 | 5 | 5 | 5 | No
C | 20 | 0 | 29 | 9 | 6 | 9 | 6 | No
D | 12 | 14 | 26 | 0 | 0 | 0 | 0 | Yes
E | 6 | 26 | 35 | 3 | 3 | 0 | 0 | No
F | 9 | 26 | 35 | 0 | 0 | 0 | 0 | Yes
END | 0 | 35 | 35 | 0 | 0 | 0 | 0 | Yes