## Penalty
Van Allen Construction Company
Late Penalty and Incentive Bonus Considered
Task | Task Duration (tj) | Immediate Predecessors | Starting Times | Finish Times | Time | Cost | Time | Cost | Slope (bj) | Marginal Cost Incr
START | 0 | - | 0 | 0
A | 5 | START | 0 | 5 | 3 | 60 | 5 | 40 | 10 | 0
B | 1 | START | 0 | 1 | 1 | 50 | 5 | 30 | 5 | 20
C | 6 | B | 1 | 7 | 5 | 70 | 10 | 40 | 6 | 24
D | 2 | A | 5 | 7 | 2 | 60 | 7 | 40 | 4 | 20
E | 6 | A | 5 | 11 | 2 | 50 | 6 | 30 | 5 | 0
F | 10 | C, D | 7 | 17 | 5 | 90 | 11 | 60 | 5 | 5
G | 6 | C, D | 7 | 13 | 4 | 60 | 6 | 30 | 15 | 0
H | 4 | G | 13 | 17 | 1 | 40 | 5 | 20 | 5 | 5
I | 4 | E, G | 13 | 17 | 1 | 50 | 4 | 20 | 10 | 0
END | 0 | F, I, H | 17 | 17 | 0 |  | 0 | 0
Totals | [5 empty] | 530 |  | 310 |  | 74
| Indirect cost/wk = | 12 |  | Exp Project Makespan |  | 19.66
| Prob of strike = | 0.7
| Penalty cost/wk = | 3.5 |  |  | Total direct cost = | 384
| Deadline = | 20 |  |  | Indirect costs = | 235.92
| Bonus/wk = | 5 |  |  | Penalty cost (3 wk str) = | 0
[5 empty] | Penalty cost (4 wk str) = | 0.735
[5 empty] | Penalty cost (5 wk str) = | 1.225
Strike |  | Expected |  | Bonus (3 wk str) = |  | 0
(wks) | Prob | Duration |  | Bonus (4 wk str) = |  | 0
3 | 0.45 | 1.35 |  | Bonus (5 wk str) = |  | 0
4 | 0.3 | 1.2 |  |  | Total cost = | 621.145
5 | 0.25 | 1.25
| E[Strike Duration] | 3.8
Crash
Normal

## No Penalty
Van Allen Construction Company
Task | Task Duration (tj) | Immediate Predecessors | Starting Times | Finish Times | Time | Cost | Time | Cost | Slope (bj) | Marginal Cost Incr
START | 0 | - | 0 | 0
A | 4 | START | 0 | 4 | 3 | 60 | 5 | 40 | 10 | 10
B | 1 | START | 0 | 1 | 1 | 50 | 5 | 30 | 5 | 20
C | 5 | B | 1 | 6 | 5 | 70 | 10 | 40 | 6 | 30
D | 2 | A | 4 | 6 | 2 | 60 | 7 | 40 | 4 | 20
E | 6 | A | 4 | 10 | 2 | 50 | 6 | 30 | 5 | 0
F | 8 | C, D | 6 | 14 | 5 | 90 | 11 | 60 | 5 | 15
G | 4 | C, D | 6 | 10 | 4 | 60 | 6 | 30 | 15 | 30
H | 4 | G | 10 | 14 | 1 | 40 | 5 | 20 | 5 | 5
I | 4 | E, G | 10 | 14 | 1 | 50 | 4 | 20 | 10 | 0
END | 0 | F, I, H | 14 | 14 | 0 |  | 0 | 0
Totals | [5 empty] | 530 |  | 310 |  | 130
| Indirect cost/wk = | 12 |  | Exp Project Makespan |  | 16.66
| Prob of strike = | 0.7
[5 empty] | Total direct cost = | 440
Strike |  | Expected |  |  | Indirect costs = | 199.92
(wks) | Prob | Duration |  |  | Total cost = | 639.92
3 | 0.45 | 1.35
4 | 0.3 | 1.2
5 | 0.25 | 1.25
| E[Strike Duration] | 3.8
Crash
Normal